## Review Template
Manazir | NFT Timeplan: Non-fungible token categorisation using machine learning classifiers
Data Science (MSc)
Loughborough University | 2022-03-01 |  |  | 2022-04-01 |  |  |  | 2022-05-01 |  |  |  |  | 2022-06-01 |  |  |  | 2022-07-01 |  |  |  | 2022-08-01
Week commencing: | 14th | 21th | 28th | 4th | 11th | 18th | 25th | 2nd | 9th | 16th | 23rd | 30th | 6th | 13th | 20th | 27th | 4th | 11th | 18th | 25th | 1st | 8th | 15th | 22nd | 29th
Task | Wk1 | Wk2 | Wk3 | Easter |  |  |  | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12 | Wk13 | Wk14 | Wk15 | Wk16 | Wk17 | Wk18 | Wk19 | Wk20 | Wk21
Progression
Project Allocation | þ
1.0 - Literature Review
General research
Initial Research - History Centralised System
Initial Research- Blockchain
Initial Research- Smart Contract
Initial Research- Etheruem
Initial Research- Crypto Punk NFT
Project Research Proposal | [8 empty] | þ
2.0 - Pre-Processing
Collecting Data using API
Cleaning Up Data
Appropriate Labeling
Storing on SQL Database
3.0 - Data Analysis
Make Hypothesis
Basic Analysis
Expereiment with different ML Algorithmns
Build Classifying Algorithm
Build CNN
Testing on Unseen data
Optimisation
Final Testing/ Prediction
4.0 - Further Work
Compare Etheureum with Bitcoin
Predict Price of Etheruem
Analsys Volume purchase of NFT
Disertation Write-up | [23 empty] | þ
Key
| þ | Hand-in
Contingency